## JIRA Backlog
Issue Type | User Story / Task | Description | Story Points | Assigned To | Branch Name | Status
Epic | Sentiment Analysis Web App | Main epic for sentiment analysis system | 0 | Project Team | - | To Do
Story | Set up the backend project structure | Initialize Flask, create virtual environment, and install required dependencies | 3 | Alice | feature/backend-setup | To Do
Task | Implement user authentication modul | Develop user signup and login functionality using MongoDB | 5 | Alice | feature/auth-module | To Do
Story | Develop audio to text conversion module | Process user audio input and convert it into text format | 5 | Bob | feature/audio-to-text | To Do
Story | Prepare input text for sentiment analysis | Clean, tokenize, and convert text into a usable format | 3 | Bob | feature/text-preprocessing | To Do
Story | Develop sentiment analysis model | Train and evaluate model for sentiment prediction | 8 | Charlie | feature/sentiment-model | To Do
Story | Create prediction API | Develop Flask API for handling sentiment prediction requests | 3 | Alice | feature/prediction-api | To Do
Story | Frontend UI | Create HTML/CSS interface for audio input and displaying results | 3 | Diana | feature/frontend-ui | To Do
Story | Implement database integration | Store user data and sentiment history using MongoDB | 3 | Alice | feature/database-integration | To Do
Story | Integrate application components | Connect frontend, backend, model, and database | 5 | Charlie | feature/system-integration | To Do
Story | Perform system testing | Conduct functional and performance testing | 3 | Diana | feature/system-testing | To Do
Task | Deploy application on Render | Deploy the complete application on Render platform | 2 | Alice | chore/render-deployment | To Do
Task | Prepare project documentation | Create SRS and final project documentation | 2 | Bob | feature/project-documentation | To Do